Activity Form

Activity						Participants		          		 Completion Date

| FIRST QUARTER – Dec 2025 -Feb 2026 |  |  |
| --- | --- | --- |
| NOGA executed – Start of Grant |  | December 1, 2025 |
| Formal agreement completed with employers/local workforce boards due |  | January 1, 2026 |
| SECOND QUARTER March-May 2026 |  |  |
| Formal Consortium Agreement submitted to THECB | Project Lead | March 1, 2026 |
| Programs are approved & in Institutional Program Inventory |  | March 1, 2026 |
| All equipment/facilities expenditures complete for limited/no equipment budgets |  | March 1, 2026 |
| 1st Interim Reports Due | Project Lead | March 6, 2026 |
| CTE Program is operational for limited/no equipment budgets |  | April 1, 2026 |
| THIRD QUARTER June-Aug 2026 |  |  |
| 2nd Interim Reports Due | Project Lead | June 5, 2026 |
| All equipment/facilities expenditures complete for medium equipment budgets |  | August 1, 2026 |
| FOURTH QUARTER Sept-Nov 2026 |  |  |
| CTE Program is operational for medium equipment budgets |  | September 1, 2026 |
| 3rd Interim Reports Due | Project Lead | September 4, 2026 |
| FIFTH QUARTER Dec 2026 -Feb 2027 |  |  |
| All equipment/facilities expenditures complete for heavy equipment budgets |  | December 1, 2026 |
| 4th Interim Reports Due | Project Lead | December 4, 2026 |
| CTE Program is operational for heavy equipment budgets |  | January 1, 2027 |
| SIXTH QUARTER March-May 2027 |  |  |
| 5th Interim Reports Due | Project Lead | March 5, 2027 |
| SEVENTH QUARTER June-Aug 2027 |  |  |
| 6th Interim Reports Due | Project Lead | June 4, 2027 |
| EIGHTH QUARTER Sept-Nov 2027 |  |  |
| 7th Interim Reports Due | Project Lead | September 3, 2027 |
| CLOSEOUT Dec 2027-March 2028 |  |  |
| Close of Grant |  | December 1, 2027 |
| Final Project & Expense Reports Due | Project Lead | February 4, 2028 |
| Unexpended funds returned |  | March 3, 2028 |